## All
Ouseburn Evidence & Measures Project, Measures Workshop 13 July 2015 | [25 empty] | RFF
PROPOSED MEASURES | [24 empty] | 1 | Confirmed urbanisation physical modification (culverts)
Group Name | [24 empty] | 3 | Suspected diffuse sewage discharge (wrong connections)
| 1. Proposed measure | [5 empty] | 2. Background |  |  | 3. Benefits |  |  |  |  | 5. Side-effects | 6. Effort |  |  |  | 7. Cost |  | 8. Comments |  |  | 4 | Confirmed point source intermittent sewage discharge
ID | Short title | Description of action (including any quantitative information if possible e.g. 5 km of fencing) | Proposer(s) | Who will take ownership of measure? (If EA or NWL, which team) | Priority : High, Med, Low | Timescale : 1 year, 2-5 years, longer | Reach | Specific location where will it be implemented? | Do you know of any other activity already addressing or partly addressing this cause (threat) in this location? | What difference (improvement) do you think this measure will make? (Include differences to the Ouseburn's ecological health, WFD or beyond, e.g. habitat, farming, birds, energy use, food production, flooding.) | Why do you think it would work? (E.g. Has it worked elsewhere) | How long before improvements are likely to be seen? | Is this measure future-proofed? (e.g. how will it change in the long term with development changes etc?) | How long do you think the measure will continue to have effect? | List any likely consequences (neutral or bad) for birds, farming, food production, flooding etc. | How long will measure take to implement? | What monitoring should we carry out before and/or after the measure has been implemented to assess the impact? | Are there opportunities to involve other stakeholders? | Do we need to do anything before the measure can start? | Estimated cost (indicative / scale) (If possible, be specific even if approximate, e.g. £10 - 20k for materials, 0.2 fte of EA time, 50 hrs of contractors time etc.) | Possible sources of funding | What might stop us implementing this measure? | Any other risks? | Any other information? | 5 | Probable point source landfill leaching
Strategic overview group
1 | Guidance for Developers | Pilot project to provide Ouseburn-specific guidance to developers about WQ requirements - Ouseburn Developers Check-list - not just 'no deterioration' of WQ but to improve WQ. Provide a checklist (for EA) and/or reach-level 'vision' to sell to developers (which will also help them sell their houses). Include info about their contribution to the big picture (to include quantifiable net benefits). NCC has guidance for developers, looking for regional SuDS guidance, to be used as a good start, will share with EA for comment as a start. Update 13th Oct 2015: This has been regionally paused. There was some guidance bringing all the local authorities together, but this required a shared approach to maintaining SUDs. This instead now sits with each local authority to work on. Could we try a joint approach again, however, it needs political support. We also need one VISION to speak with one voice to developers. This links also to the Lead Local Flood Authority. | Cameron Sked / Maria Hardy | NCC to provide existing guidance (Darren Varley this week), EA (Maria Hardy) will review; together to make reach-specific guidance via EA's Ouseburn catchment group inviting relevant external people (NCC Planners and John Robinson/Darren Varley, NWL Les Hall's team, plus TRT) by late September / site walkovers by end October |  |  | Target Reach 2 to start with | Target developments around Callerton to start with | No, only existing guidance and no Ouseburn-sepcific | Future protection of the river by influencing the planning agenda
2 | Engage with LNP | Identify who key stakeholders are for the Ouseburn, including any LNP, and engage with them | Cameron Sked | Cameron Sked
3 | Finalise Ouseburn SWM Plan | Ouseburn Surface Water Management Plan - Steering Group meeting to include NCC/NWL (Les Hall and Laura Clegg)/EA. To agree how to approach developers on surface water management plan. To consider emphasising that developments should make a feature of rivers, with space for them. Highlight opportunities and issues on a select few sites (starting with Callerton - one landowner but several rival developers) to influence developers' Master Plan. | Darren Varley | Darren Varley (convenes Steering Group) |  |  | Reach 2 | Callerton sites to start with |  | Future protection of the river by influencing the planning agenda
4 | Reduce housing inputs to sewerage system | We should identify opportunities to remove surface water inputs to the sewer system as part of new/re-development to reduce pressure on CSOs (Kenton Bank Foot work with current developer as example). Link back to Ouseburn Developers Check-list. Update 13th Oct 2015 This is ongoing / already happening. The picture constantly changes. About developer guidance there was a document being drawn together by Gateshead, but as this involved SUDs maintenance (which is different in each local authority) it is still up to each local authority to adopt. |  | NWL and Newc City Council |  |  | Reaches 2, 3, 4 | Opportunistic |  | Future protection of the river by influencing the planning agenda
5 | Misconnections prevention | Work to prevent misconnections - coloured pipes clearly labelled? Can we research if this has been done elsewhere? | Susan Mackirdy | NWL (Sue H) |  |  |  | New development sites
6 | Pre-development sediment management | On greenfield sites : pre-planting, vegetation establishment and earth-handling strategies : to prevent release of phosphate bound up in sediments. Raise awareness with developers and planners for need to manage sediments and prevent them reaching watercourses - consider for Ouseburn Developers Check-list. |  | linked to Item 1
7 | P Source Apportionment | Investigate whether we can quantify the phosphate impacts at certain sites - crude source apportionment assessment - to help understand nature of P (e.g. bound up in sediments) to help with prioritisation of management actions and polluter pay actions | Sue Horsley | Susan Mackirdy to do initial investigation |  |  | Not reach-specific
8 | Senior level buy in and support | Continued co-ordination of action and buy in / support at senior level in relevant organisations to see this project through (pick up in Next Steps discussion). Need to write up the Evidence & Measures project as a starting point. 1 page briefing note for senior managers (signed up to by all organisations). | Susan Mackirdy | Susan Mackirdy to prepare a short briefing note and circulate to workshop attendees (by end this week). Also to get funding to write up E&M project. |  | Underway | Whole of the Ouseburn
9 | Ouseburn-specific planning training | Influence the Planning Committee members to understand the importance of pollution mitigation measures (and non-dangers of SuDS). EA has a training package it will share. Should use Great Park as a good example. | Susan Mackirdy | Cameron Sked to share training package, Darren to include in planning training day (upcoming) with NCC and North Tyneside and Regional SuDS Group. [How do we get out to members?] |  |  | Not reach-specific
Waste Water Group
10 | Re-lay Brunton Lane sewer | Re-lay the sewer to address what has been previous discharge into the Ouseburn. Keep on monitoring pollution levels as sewer is replaced. | Tony Baines | NWL |  |  | Reach 4 | Brunton lane sewer | NWL, Brunton Lane sewer plans | Reduce risk of future pollution incidents |  | 12-24 months | Plans will be reviewed in discussion with developers. |  |  | within 24 months |  | Planners and developers | Try to optimise scheme in discussion with developers |  | NWL amp6 funding
11 | Investigate outfall misconnections 1 | Review location of misconnections in the Kingston Park outfall catchment of the last 10 years to identify any areas which are worse than others. | Rob Carr | ? |  |  | Reach 4 | Kingston Park outfall catchment | Ongoing NWL reaction misconnection team | Help with yellow fish campaign with communtiies
12 | Investigate outfall misconnections 2 | Increase monitoring within catchment area. | Rob Carr | ? |  |  | Reach 4 | Kingston Park outfall catchment | Ongoing NWL reaction misconnection team | Reduce frequency of misconnections
13 | Investigate outfall misconnections 3 | "Daylighting" parts of culvert so that people can see pollution at points other than outfall | Rob Carr | ? |  |  | Reach 4 | Kingston Park outfall catchment | Ongoing NWL reaction misconnection team | Reduce frequency of misconnections
14 | Investigate outfall misconnections 4 | Install water quality logger downstream of Kingston Park outfall | Nick Rukin | EA |  |  | Reach 4 | Kingston Park outfall catchment | Ongoing NWL reaction misconnection team | Reduce frequency of misconnections
15 | Investigate outfall misconnections 5 | Consider a community action plan. | Linzie Pentleton | NWL |  |  | Reach 4 | Kingston Park outfall catchment | Ongoing NWL reaction misconnection team | Reduce frequency of misconnections
16 | Investigate outfall misconnections 6 | End of surface water pipe treatment. Possible disconnections further upstream. | Claire Deasy | ? |  |  | Reach 4 | Kingston Park outfall catchment | Ongoing NWL reaction misconnection team | Reduce frequency of misconnections | [7 empty] | Links with natural flood management teams, potential wildlife trust.
17 | A1 Run-off to outfall investigation | Investigate likely and actual water quality to the outfall east of the A1. Check with highways agency on catchment to the outfall. Sample outfall water quality (for phosphates, ammonia, foecal coliforms and chloride) under a range of flows. | Tony Baines, Nick Rukin | EA |  |  | Reach 4 | Outfalls to the east of the A1 | No | Rule in or out this outfall as a major phosphate source | [7 empty] | Highways agency.
18 | Outfall water quality attenuation | Consider use of attenuation mattresses at outfalls to improve quality of water. ("magic" matresses, different mediums) Update 13th Oct 2015: maintenance issues, trials with United Utilities, Rob Carr will find out more / costs | Rob Carr | ? |  |  | All Reaches | Problematic outfalls | No | Improve water quality
19 | Generic actions in all reaches | Awareness campaign for golf courses, race course and parkland on managing phosphates. Liaise with Newcastle City Council allotments officer regarding allotments. Link to land management group | Rob Carr | ? |  |  | All Reaches | Golf courses, race courses and parkland | No | On the basis of EA National advice phosphate contributions from golf courses are thought to be small unless they are new or being built, so in theory it might not make much difference.
20 | Killingworth - Long Benton sustainable drainage plan 1 | Taking out Killingworth lake and Long Benton letch from Ouseburn catchment (flooding). | Linzie Pentleton | NWL |  | Ongoing; has been out to consultation | Reach 5 | Killingworth lake and Long Benton letch | No | Free up the capacity of sewers. Should reduce spills. Add to diluting P to White Moor tributary. |  | During Amp6 (2020) |  |  |  | During Amp6 (before 2020)
21 | Killingworth - Long Benton sustainable drainage plan 2 | Pre-measure monitoring. Routine monthly monitoring where scheme currently discharges and prior to the confluence with the Ouseburn. The Killingworth / Long Benton Sustainable Drainage Plan will make a big difference and so should be taking into account when thinking about additional measures. Need some monitoring before and after the scheme so stakeholders can learn how the scheme affects water quality. Especially where the scheme currently discharges and also before it meets the Ouseburn. Update 13th Oct 2015: Would be a good idea. "modelling" hasn't had any water quality. Is this a research project? We need a suite of research ideas - separate group, Clare to lead. S106 has to be linked to the development itself. | Nick Rukin | EA; N Tyneside Council; Mark Newlands? |  |  | Reach 5 | See description of action. | No | Reduce potential pollution.
22 | Bushy Park monitoring | Bushy Park stream; reinstate water quality monitoring for 12 month period at Salter's Close monitoring point. | Nick Rukin, Rob Carr | EA |  |  | Reach 5 | Salter's Close monitoring point | surface water outflow investigation (NWL) | Rule in or out this tributary as a major phosphate source
23 | Reach 5 monitoring | Targeted water quality monitoring. Add additional monitoring points along Ouseburn and tributaries between Three Mile Bridge and Castle Farm Bridge for 12 month period. | Nick Rukin, Rob Carr | EA |  |  | Reach 5 | to be confirmed but taking into account tributaries. | No | Will tell us the largest change in water quality occurs along that stretch of the catchment.
24 | Septic tank per reach estimate | NWL to calculate number of properties in each reach likely to be on septic tank using the numbers of those on water supply but not on sewage network. | Rob Carr | NWL (Linzie Pentleton) |  |  | All Reaches | All reaches | No | Will tell us whether septic tanks are a big or small problem in each reach | [8 empty] | E and M team to send NWL the reach catchment areas.
25 | Private STWs inspection | EA to inspect operation of private sewage treatment works. | Rob Carr | EA |  |  | Reach 5 (Other reaches if shown to be important) | At consented STW | No | Checking STWs dischargers are as designed | [5 empty] | 12 months
26 | Reach 5 tributary loading | Use monitoring data and estimates of flows on tributaries to work out the loading to the Ouseburn | Nick Rukin, Claire Deasy | EA |  |  | Reach 5 | At monitored reaches | No | Help work out where the worst problems are
27 | North Walbottle telemetry data for spills | Comparison of spill data with water quality data to rule in or out North Walbottle station as a threat | Rob Carr | Rob Carr, Tony Baines |  | Can be 'business as usual' | Reach 1 | North Walbottle PS outfall | NWL improvement over past 5 years | Rule in or out North Walbottle as a threat. | [8 empty] | NWL (Tony Baines) to provide telemetry data for spills form 2010 onwards
28 | Stamfordham telemetry data for spills | Comparison of spill data with water quality data to rule in or out Stamfordham station as a threat | Rob Carr | Rob Carr, Tony Baines |  | Can be 'business as usual' | Reach 1 | Stanfordham PS outfall | NWL improvement over past 5 years | Rule in or out Stanfordham as a threat.
29 | Private STWs inspection | EA to inspect operation of private sewage treatment works. | Rob Carr | EA |  |  | Reach 2 | At consented STW | No | Checking STWs dischargers are as designed
30 | Surface water outfall inspection | Whorlton Hall, Newcastle Chapel Park and Woolsington inspect outfalls for evidence of misconnections and spot sample. | Nick Rukin, Rob Carr | Rob Carr |  |  | Reach 2 | Surface water outfalls as mentioned | NWL misconnections team | Keeping a check on misconnections where public access limits public reporting
31 | CSO monitoring data review meeting | NWL to bring CSO monitoring data to review in discussion with EA monitoring data around CSOs. To check that CSOs are working as designed. Meeting every 6-12 months. Any pollution incident data to be brought to the meetings. | Rob Carr | Rob Carr/Linzie Pentleton |  |  | All Reaches | CSO locations | No | Checking CSOs are not a significant part of P load or short term ammonia spike
Agriculture land MGT group
32 | Land use survey 1 | Detailed assessment of land use in catchment (Ha of what is arable, grassland, livestock). Engagment with land owners, - NE needs to be engaged to access land ownership data |  | Natural England and Environment Agency (NE depends on priorities and resources) |  |  | Reach 1 | Basic overview of area | No | To assess where issues/hotspots are, leading to a reduction in phosphate by then implementing other measures | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
33 | Land use survey 2 | Detailed assessment of land use in catchment (Ha of what is arable, grassland, livestock). Engagment with land owners, - NE needs to be engaged to access land ownership data |  | Natural England and Environment Agency (NE depends on priorities and resources) |  |  | Reach 2 | ? - Paul Muto may be able to provide information - Dairy Farm and Black Callerton Farm may be main culprits. | No | To assess where issues/hotspots are, leading to a reduction in phosphate by then implementing other measures | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
34 | Land use survey 3 | Detailed assessment of land use in catchment (Ha of what is arable, grassland, livestock). Engagment with land owners, - NE needs to be engaged to access land ownership data |  | Natural England and Environment Agency (NE depends on priorities and resources) |  |  | Reach 4 | ? - Paul Muto may be able to provide information | No | To assess where issues/hotspots are, leading to a reduction in phosphate by then implementing other measures | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
35 | Land use survey 4 | Detailed assessment of land use in catchment (Ha of what is arable, grassland, livestock). Engagment with land owners, - NE needs to be engaged to access land ownership data. See row 56 / 57 |  | Natural England and Environment Agency (NE depends on priorities and resources) |  |  | Reach 5 | ? - Paul Muto may be able to provide information | No | To assess where issues/hotspots are, leading to a reduction in phosphate by then implementing other measures | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
36 | Soil testing | Soil testing. Is there a historical build up of phosphate in the sediment? Is the watercourse originating from a embedded high phosphate area? Could this be a Masters Student project to map phosphate. |  | Masters project or part of upper Ouseburn project (EA) |  |  | Reach 1 | All of the reach | Not that we know of | Help make the ag investigations into a project so EA, NE etc can put in resources | [6 empty] | 1 year to begin to collect information | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
37 | Watercourse sediment testing | Phosphorus sediment of the watercourse testing. Again is this embedded historical phophorus or run off? |  | Masters project or part of upper Ouseburn project (EA) |  |  | Reach 1 | All of the watercourse in the reach | Not that we know of | Help make the ag investigations into a project so EA, NE etc can put in resources | [6 empty] | 1 year to begin to collect information | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
38 | Walkover survey and mapping of watercourse 1 | Survey and map all the tributaries, monitor for heavy loading on tributaries allows to eliminate some branches. Mapping of field drains and where phosphate is leaching from |  | Environment Agency - Environment Officers, Tyne Rivers Trust |  |  | Reach 1 | Use confluences of tributaries as monitoring points to reduce walkover time, winter time monitoring | Environment Agency EO's may have information | Help make the ag investigations into a project so EA, NE etc can put in resources | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
39 | Digitising of all Ouseburn information | Collating all information related to the Ouseburn e.g measures already completed, surveys, data collected |  | Masters project or part of upper Ouseburn project (EA) |  |  | Reach 1 | All of the reach | Tyne Rivers Trust have started collecting this information with the E&M project | [8 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
40 | Walkover survey and mapping of watercourse 2 | Survey and map all the tributaries, monitor for heavy loading on tributaries allows to eliminate some branches. Mapping of field drains and where phosphate is leaching from |  | Environment Agency - Environment Officers |  |  | Reach 2 | Use confluences of tributaries as monitoring points to reduce walkover time, winter time monitoring | Environment Agency EO's may have information | Help make the ag investigations into a project so EA, NE etc can put in resources | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
41 | Digitising of all Ouseburn information | Collating all information related to the Ouseburn e.g measures already completed, surveys, data collected |  | Masters project or part of upper Ouseburn project (EA) |  |  | Reach 2 | Reach wide scheme | Tyne Rivers Trust have started collecting this information with the E&M project | [8 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
42 | Watercourse sediment testing | Phosphorus sediment of the watercourse testing. Again is this embedded historical phophorus or run off? |  | Masters project or part of upper Ouseburn project (EA) |  |  | Reach 2 | All of the watercourse in the reach | Not that we know of | Help make the ag investigations into a project so EA, NE etc can put in resources | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
43 | Walkover survey and mapping of watercourse 3 | Survey and map all the tributaries, monitor for heavy loading on tributaries allows to eliminate some branches. Mapping of field drains and where phosphate is leaching from DOES THIS DUPLICATE ROW 41? |  | Environment Agency - Environment Officers, Tyne Rivers Trust |  |  | Reach 2 | Use confluences of tributaries as monitoring points to reduce walkover time | Environment Agency EO's may have information | Help make the ag investigations into a project so EA, NE etc can put in resources | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
44 | Manure heap survey | Mapping all manure heaps along watercourse, can be done by driving around the area or walking watercourse. Engagement with farmers - best practice with siting of heaps away from watercourse, not over field drains. |  | Natural England, depends on priorities and resources. Ideally part of bigger upper Ouseburn project |  |  | Reach 2 | Reach wide scheme, black callerton is a good starting point | Not that we know of | Help make the ag investigations into a project so EA, NE etc can put in resources | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
45 | Farm run off survey 1 | Mapping issues, disconnected down pipes, run off from hard standing |  | Natural England, depends on priorities and resources. Ideally part of bigger upper Ouseburn project |  |  | Reach 1 | Reach wide scheme | Not that we know of | Help make the ag investigations into a project so EA, NE etc can put in resources | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
46 | Farm run off survey 2 | Mapping issues, disconnected down pipes, run off from hard standing |  | Natural England, depends on priorities and resources. Ideally part of bigger upper Ouseburn project |  |  | Reach 2 | Reach wide scheme | Not that we know of | Help make the ag investigations into a project so EA, NE etc can put in resources | [7 empty] | Farm Scoper (nutrients and pesticides) - David Johnson from National Rivers Trust, using Adas tool to engage landowners
47 | Golf course investigation 1 - reach 4 | Golf courses investigation, EO's to go out and collect evidence to support/refute that established golf courses don't contribute much phosphorus to the watercourse - only needs to be simple water quality testing. Do surrounding waterbodies/features appear green? discussions with green keepers |  | Environment Agency |  | Can be 'business as usual'. EA and NE officers working together in a co-ordinated way. Would need the Ouseburn to be a focus for Natural England, senior-level support. | Reach 4 |  |  | Rule this threat in or out |  | it will take one day of EO's time
48 | Golf course investigation 2 - reach 5 | Golf courses investigation, EO's to go out and collect evidence to support/refute that established golf courses don't contribute much phoshorus to the watercourse - only needs to be simple water quality testing. Do surrounding waterbodies/features appear green? discussions with green keepers |  | Environment Agency |  | Can be 'business as usual'. EA and NE officers working together in a co-ordinated way. Would need the Ouseburn to be a focus for Natural England, senior-level support. | Reach 5 |  |  | Rule this threat in or out |  | it will take one day of EO's time
49 | Golf course investigation 3 = reach 2 | Golf courses investigation, EO's to go out and collect evidence to support/refute that established golf courses don't contribute much phoshorus to the watercourse - only needs to be simple water quality testing. Do surrounding waterbodies/features appear green? discussions with green keepers |  | Environment Agency |  | Can be 'business as usual'. EA and NE officers working together in a co-ordinated way. Would need the Ouseburn to be a focus for Natural England, senior-level support. | Reach 2 |  |  | Rule this threat in or out
50 | Golf courses (2) & race course investigation - reach 5 | EO's to visit and ask what thier nutrient regime is and do they do any testing to rule in or out. EO's to go out and collect evidence to support/refute that established golf courses don't contribute much phoshorus to the watercourse - only needs to be simple water quality testing. Do surrounding waterbodies/features appear green? discussions with green keepers | Mary Weatherby (EA) | Environment Agency |  | Can be 'business as usual'. EA and NE officers working together in a co-ordinated way. Would need the Ouseburn to be a focus for Natural England, senior-level support. | Reach 5 | Golf course & racecourse | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
51 | Gosforth Lake investigation | Sampling of water entering & leaving Gosforth Lake (private nature reserve) to see if there is stored P in sediment. Also sample West Moor trib. Sample in dry conditions and affter heavy rain. Check EA P samples in 2010/2011 (P 15 - P25). Update 13th Oct 2015: Emma has some data from Natural History Society, they would like more testing | Emma Craig (NWT) | Northumbria Natural History Society |  |  | Reach 5 | At outfall & entry point to lake | ACTION: E Craig to ask N Hist Society if they have done sampling | Rule this threat in or out |  |  | Liaise with policy in terms of impact development has on green space |  |  | 1 day's work |  |  |  | Initial investigation only 1 - 2 days
52 | Agricultural investigation | WQ sampling for P for nearby agricultural land | Paul Muto (NE) | EA & NE? |  |  | Reach 5 | At specific poiunts to separate out the signal from agricultural land | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
53 | Trib investigation | Investigations on Gosforth Letch - similar to Gosforth Lake investigations, row ID 51 | Emma Craig (NWT) | EA & NE? |  |  | Reach 5 |  | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
54 | Farm visits 1 | Visit farms to discuss nutrient management (perhaps use Farm Scoper as a tool) | Paul Muto (NE) | EA & NE? |  |  | Reach 5 | Extreme NW of Reach 5 | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
55 | Farm visits 2 | Visit farms to discuss nutrient management (perhaps use Farm Scoper as a tool) | Paul Muto (NE) | EA & NE? |  |  | Reach 5 | Middle of Reach 5 | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
56 | Land use survey 1 | Similar to row ID 32 (Detailed assessment of land use in catchment) | Paul Muto (NE) | EA & NE? |  |  | Reach 5 | Extreme NW of Reach 5 | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
57 | Land use survey 2 | Similar to row ID 32 (Detailed assessment of land use in catchment) | Paul Muto (NE) | EA & NE? |  |  | Reach 5 | Middle of Reach 5 | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
58 | Sampling at Gt Park & agricultural area | Set up the sampling so as to be able to distinguish between inputs from the Great Park cells with the arable fields in the far NE of Reach 5 | Mary Weatherby (EA) | EA & NE? |  |  | Reach 5 |  | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
59 | Sampling at Nunns Moor & Dukes Moor | Sampling inputs from this agricultural area (livestock) - to rule it in or out (for completeness so lower priority than other areas in Reach 5) | Mary Weatherby (EA) | EA & NE? |  |  | Reach 5 | At northern end of moor just before drainage enters the trib of the Ouseburn | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
60 | Monitoring during construction phase of development 1 | To minimise P sediments from erosion (should be picked up by Strategy Gp) | Paul Muto (NE) | EA & NE? |  |  | Reach 5 |  | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
61 | Monitoring during construction phase of development 2 | To minimise P sediments from erosion (should be picked up by Strategy Gp) | Paul Muto (NE) | EA & NE? |  |  | Reach 5 |  | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
62 | Trib investigation | Investigations on West Moor trib - similar to row ID 51 (sampling) | Emma Craig (NWT) | EA & NE? |  |  | Reach 5 |  | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
63 | Golf course investigation | Same as row ID 50 (EO's visit) | Mary Weatherby (EA) | EA & NE? |  |  | Reach 4 | City of Newcastle Golf Course | No | Rule this threat in or out | [9 empty] | Initial investigation only 1 - 2 days
64 | Defra support 1 | Raise with Defra the issue of diffuse agricultural issues in the urban fringe. Can Defra lend support to the agricultural investigation | Paul Hulme (pjHYDRO) | EA & NE? |  |  | Reach 4 | ag area | No | Help make the ag investigations into a project so EA, NE etc can put in resources
65 | Defra support 2 | Same as row ID 64 (Defra support) | Paul Hulme (pjHYDRO) | EA & NE? |  |  | Reach 1 | ag area | No | Help make the ag investigations into a project so EA, NE etc can put in resources
66 | Defra support 3 | Same as row ID 64 (Defra support) | Paul Hulme (pjHYDRO) | EA & NE? |  |  | Reach 2 | ag area | No | Help make the ag investigations into a project so EA, NE etc can put in resources
67 | Defra support 4 | Same as row ID 64 (Defra support) | Paul Hulme (pjHYDRO) | EA & NE? |  |  | Reach 5 | ag area | No | Help make the ag investigations into a project so EA, NE etc can put in resources
68 | Investigate drainage patterns in ag areas | To understand drainage in the agricultural areas that are left after development - but what are timescales for development? Is this a priority if the development is going to happen. What hydrological regime will be left after the development. Priority to liaise with people who are involved in development (J Robinson & C Sked) and get this included in development masterplan. | Mary Weatherby (EA) | EA |  |  | Reach 4 | ag area | No |  |  |  | High pressures on green apcde over the next 20 years. Liaise with policy in terms of impact development has on green space
Note on C22: TyneCatchment: Ask Nick to expand
Note on E15: TyneCatchment: Ask Cameron for update
Note on K5: Note: bad consequences are listed later (col N).

## pivoted headings
ID
Short title
Description of action (including any quantitative information if possible e.g. 5 km of fencing)
Proposer(s)
Who will take ownership of measure? (If EA or NWL, which team)
Reach
Specific location where will it be implemented?
Do you know of any other activity already addressing or partly addressing this cause (threat) in this location?
What difference (improvement) do you think this measure will make? (Include differences to the Ouseburn's ecological health, WFD or beyond, e.g. habitat, farming, birds, energy use, food production, flooding.)
Why do you think it would work? (E.g. Has it worked elsewhere)
How long before improvements are likely to be seen?
Is this measure future-proofed? (e.g. how will it change in the long term with development changes etc?)
How long do you think the measure will continue to have effect?
List any likely consequences (neutral or bad) for birds, farming, food production, flooding etc.
How long will measure take to implement?
What monitoring should we carry out before and/or after the measure has been implemented to assess the impact?
Are there opportunities to involve other stakeholders?
Do we need to do anything before the measure can start?
Estimated cost (indicative / scale) (If possible, be specific even if approximate, e.g. £10 - 20k for materials, 0.2 fte of EA time, 50 hrs of contractors time etc.)
Possible sources of funding
What might stop us implementing this measure?
Any other risks?
Any other information?
Note on A9: Note: bad consequences are listed later (col N).

## Sheet2
Darren Varley, NCC | Ouseburn surface water management plan | A lot of baseline data. Model developed for 2030 scenario (development, growth, creep, climate change) shows increased flows and depths in the Ouseburn.
Have identified potential options to mitigate these increases (not quite finalised but will share when available).
Group has prioritised the list of mitigation options - 3 priorities - and costings. High figure. Developers saw it as a magic bullet but it is more about a strategy for master planning.
Aim to keep flows to 2015 levels. Need to work with developers as a whole, not individuals. Will send proposals back to developers.
Looking to store surface water and hold it back in certain areas (Brunton Bridge Farm) but may be insurmountable land issues. Red House Farm (Gosforth) for potential storage. Surface sewer at Kingston Park separation. North Callerton development areas SuDS plus some opportunities for storage outside of the site (Duke of Northumberland land - amenable?).
Trying to get threse principles embedded in developers' plans.
Developers will still need to manage storage on each site as well.
Maria Hardy, EA |  | Lots of small interventions add up.
Cameron Sked, EA |  | Need to ensure these sites manage water quality impacts as well as flood management.
John Robinson, NCC |  | Onus will be on the developer to identify the appropriate site(s).
Cameron Sked, EA |  | Community Infrastructure Levy looks at strategic infrastructure needs. Are developers looking to get their applications in before CIL?
John Robinson |  | One development in already, other developers are anxious to get applications in to test the water.
Cameron Sked, EA |  | Need to get actions into the CIL 'list' (includes infrastructure such as schools).
Darren Varley, EA |  | Steering Group is bringing all this together; learning process for developers.
Maria Hardy, EA |  | Space is needed for what we want to achieve - recent application managed this by prioritising green space along the river.
Cameron Sked, EA |  | Developers are not so up to speed or comfortable with addressing WQ issues.
John Robinson |  | Industrial development sites near airport 46ha of employment-related sites - opportunities for water management (especially because lower density).